## Risk Register
CYBER RISK REGISTER — FENSIS LIMITED
Framework: NIST CSF 2.0 ¦ Assessment Method: Desk-Based Review ¦ Period: Dec 2025 – Mar 2026 ¦ Consultant: Breck Agyekum
CRITICAL — Score 20 to 25 ¦ Immediate action required |  |  | HIGH — Score 15 to 19 ¦ Action within 30–90 days |  |  | MEDIUM — Score 8 to 14 ¦ Action within 90–180 days |  |  | LOW — Score 1 to 7 ¦ Monitor and review annually
Risk ID | Asset | Risk Scenario | Threat | Vulnerability | L | I | Score | Rating | Risk Owner | Current Control | Control Gap | Recommended Action | Priority
R-01 | Customer Records & Site Information | Customer records or site layouts stolen or exposed — physical safety risk to clients | Records stolen, leaked, or sent to wrong person — used to target client property | No access control policy. No data handling procedure. Records on personal devices and WhatsApp. | 4 | 5 | 20 | CRITICAL | Operations Manager | Informal only. Records handled by staff without formal policy. Cybersecurity concerns referred to IT ad hoc. | No access control policy, data classification, device management policy, or data handling training. | Develop customer data handling policy covering storage, access, sharing, and disposal. Owner: Operations Manager. Timeline: 30 days. Cost: Zero. | Phase 1 0–30 days
R-02 | Supplier & Vendor Relationships | Vendor supply disrupted or geopolitical restrictions affect product availability | Key supplier stops supplying or geopolitical restrictions on Hikvision and Dahua extend to Ghana | Over-reliance on few vendors. No backup supplier. No vendor risk assessment. No contingency plan. | 5 | 5 | 25 | CRITICAL | Managing Director / Procurement Manager | No formal control. Vendor dependency managed through normal purchasing decisions only. | No vendor risk assessment, backup supplier list, substitution process, or supply disruption plan. | Create backup vendor and product substitution plan. Formally disclose Hikvision and Dahua geopolitical risk to leadership. Owner: MD / Procurement. Timeline: 30 days. | Phase 1 0–30 days
R-03 | Company Reputation & Brand Image | Reputation damaged by public incident, failed installation, or fake products | Failed installation, public complaint, fake products, or social media used to scam clients | High-trust market. Complaint handling is informal and case by case. No public response protocol. | 4 | 4 | 16 | HIGH | Managing Director | Informal only. Complaints handled case by case by staff or management without formal procedure. | No formal complaint escalation, service recovery procedure, public response protocol, or reputation monitoring. | Implement complaint handling and escalation procedure with response timelines. Owner: MD. Timeline: 45 days. | Phase 2 30–90 days
R-04 | Skilled Technicians & Staff | Technician makes serious error or leaves suddenly taking critical knowledge | Technician error, safety step ignored, or sudden departure with undocumented knowledge | Knowledge in heads not documents. Gaps in supervision. Inconsistent training follow-through. | 4 | 4 | 16 | HIGH | Technical Manager / HR Manager | Informal only. Work depends on individual skill and supervisor oversight where available. | No QA checklist, peer review process, error reporting procedure, or backup technician plan. | Introduce standard installation and QA checklist for all jobs before sign-off. Owner: Technical Manager. Timeline: 45 days. | Phase 2 30–90 days
R-05 | Technical Knowledge & Training | Training stops, becomes outdated, or remains undocumented | Training stops or stays only with experienced staff causing errors and inconsistent service | No documented procedures or checklists. Training not maintained consistently. Over-dependence on individuals. | 4 | 4 | 16 | HIGH | Technical Manager | Informal only. Training relies on experience, periodic knowledge sharing, and senior technician guidance. | No training schedule, training records, refresher program, product update process, or documented procedures. | Create technician training register and refresher schedule covering product updates, safety, and installation standards. Owner: Technical Manager. Timeline: 60 days. | Phase 2 30–90 days
R-06 | Website, Email & Social Media | Email or social media account hacked, taken over, or impersonated | Email hacked, company impersonated, social media taken over — used to scam clients or damage brand | No MFA. No password policy. Public-facing channels make targeting easy. Weak or reused passwords. | 4 | 4 | 16 | HIGH | Admin / IT Manager | IT referral only. Issues handled reactively after problems occur through IT or account recovery. | No MFA requirement, password policy, social media access control, monitoring, or incident response procedure. | Enforce MFA and controlled account access on all business email and social media. Owner: IT Manager. Timeline: 7 days. Cost: Zero. | Phase 2 30–90 days
R-07 | Financial Records & Business Data | Financial records altered, hidden, or leaked through weak internal controls | Financial records altered, hidden, or leaked — leading to fraud, wrong decisions, or payment issues | One person too much control. No segregation of duties. Records in spreadsheets and email attachments. | 4 | 5 | 20 | CRITICAL | Finance Manager / Managing Director | Informal only. Financial records managed through manual records, spreadsheets, and staff responsibility. | No segregation of duties, approval workflow, access restriction, reconciliation schedule, or audit trail. | Implement basic financial control procedure requiring approvals, restricted access, and monthly reconciliation. Owner: MD / Finance Manager. Timeline: 30 days. | Phase 1 0–30 days
R-08 | Project & Installation Records | Project files lost, exposed, or uncontrolled after project completion | Project files lost, accessed by wrong person, or left behind on personal devices after completion | No archiving policy. Records on WhatsApp and personal devices. No clear ownership post-completion. | 4 | 4 | 16 | HIGH | Operations / Project Manager | Informal only. Records stored and shared through phones, WhatsApp, emails, paper notes, and spreadsheets. | No centralised record system, file naming standard, version control, access control, or backup procedure. | Establish centralised project documentation folder with naming standards, access rights, and backup rules. Owner: Operations Manager. Timeline: 60 days. | Phase 2 30–90 days
R-09 | Inventory & Product Stock | Stock stolen, damaged, or replaced with counterfeit products | Products stolen, damaged, mixed with counterfeits, or delayed before reaching client | Weak storage control. Poor stock tracking. Limited inspection at receiving and dispatch. | 3 | 4 | 12 | MEDIUM | Warehouse / Procurement Manager | Informal only. Inventory checks depend on staff observation, supplier trust, and manual stock counts. | No receiving inspection checklist, supplier verification process, stock reconciliation, or counterfeit detection. | Introduce stock receiving and verification checklist to confirm authenticity, condition, and quantity. Owner: Warehouse Manager. Timeline: 90 days. | Phase 3 90–180 days
R-10 | Sales, Contracts & Pricing Data | Commercial data accessed by wrong person internally or externally | Staff or outsider accesses quotations, contracts, or pricing — giving competitors advantage | Too many people with access. Commercial data shared through email, shared folders, and printed copies. | 4 | 4 | 16 | HIGH | Sales Manager / Managing Director | Informal only. Pricing and contracts shared among sales, finance, and operations without restrictions. | No commercial data classification, role-based access, quotation approval workflow, or offboarding process. | Implement role-based access and quotation approval controls for pricing, contracts, and quotations. Owner: Sales Manager / MD. Timeline: 60 days. | Phase 2 30–90 days
SUMMARY |  |  |  |  | CRITICAL: 3 risks |  | HIGH: 6 risks |  | MEDIUM: 1 risk |  | LOW: 0 risks |  | 10 Total
Fensis Limited ¦ Cybersecurity Strategy and GRC Improvement Roadmap ¦ NIST CSF 2.0 ¦ Breck Agyekum — GRC Consultant ¦ Dec 2025 – Mar 2026