## GRC Roadmap
GRC IMPROVEMENT ROADMAP — FENSIS LIMITED
Cybersecurity Strategy and GRC Improvement Roadmap ¦ Framework: NIST CSF 2.0 ¦ Period: Dec 2025 – Mar 2026 ¦ Consultant: Breck Agyekum
PHASE 1 — 0 to 30 Days ¦ Stop the Bleeding |  |  | PHASE 2 — 30 to 90 Days ¦ Build the Foundation |  |  | PHASE 3 — 90 to 180 Days ¦ Strengthen and Sustain
ID | Function | Control Description | Owner | NIST CSF Ref | Timeline | Recurring | Phase | Priority
GV-01 | Govern | Assign Operations Manager or General Manager as named Cybersecurity Risk Owner with defined responsibilities and accountability for the GRC programme | MD / Board | GV.RR-01, GV.RR-02 | Days 1–7 | No | Phase 1 | CRITICAL
PR-01 | Protect | Enable MFA on all business accounts — email, social media, ERP, finance, and admin. Introduce password policy requiring strong unique passwords, no sharing, and immediate change on staff departure | IT Manager | PR.AA-03, PR.AA-05 | Days 1–7 | No | Phase 1 | CRITICAL
RC-01 | Recover | Move all critical records to approved cloud storage with role-based access. Establish weekly backup routine and quarterly restoration testing to verify recovery works | Risk Owner / IT | RC.RP-01, RC.RP-02 | Days 1–30 | Yes — Weekly | Phase 1 | CRITICAL
ID-01 | Identify | Formalise and maintain the asset register quarterly and after any major business change — new supplier, new system, role change, or new type of customer record | Operations Manager | ID.AM-01, ID.AM-05 | Days 1–30 | Yes — Quarterly | Phase 1 | HIGH
DE-02 | Detect | Create a one-page cybersecurity incident reporting guide specifying who to contact, what to report, and how quickly. Distribute via WhatsApp, printed copies, and shared drive | Risk Owner | DE.AE-02 | Days 1–30 | No | Phase 1 | HIGH
RS-01 | Respond | Create a one-page incident response plan covering: report, contain, identify, escalate, contact IT, document, and review. Distribute to all staff | Risk Owner | RS.MA-01, RS.MA-02 | Days 1–30 | Yes — Annual review | Phase 1 | HIGH
GV-02 | Govern | Develop and approve Information Security and Data Handling Policy covering storage, access, sharing, disposal of sensitive information, and device use expectations | Risk Owner | GV.PO-01, GV.PO-02 | Days 30–60 | Yes — Annual review | Phase 2 | HIGH
PR-02 | Protect | Implement technician device-use policy requiring approved storage, screen locks, device encryption, approved cloud backup, and remote wipe capability for all staff handling customer site information | Technical Manager | PR.AA-05, PR.DS-01 | Days 30–60 | No | Phase 2 | HIGH
PR-03 | Protect | Implement role-based access control — restrict finance, contracts, customer records, and admin accounts to approved roles. Review access quarterly and remove immediately on staff departure | Operations Manager | PR.AA-05 | Days 30–60 | Yes — Quarterly | Phase 2 | HIGH
DE-01 | Detect | Enable built-in security alerts — suspicious logins, new device sign-ins, failed attempts, account recovery changes. Risk Owner reviews alerts weekly | IT Manager | DE.CM-01, DE.CM-09 | Days 30–45 | Yes — Weekly | Phase 2 | HIGH
ID-02 | Identify | Create vendor dependency register for Hikvision, Dahua, Nemtek, and Centurion covering supply risk, business dependency, alternatives, and geopolitical concerns. Review HIGH-risk vendors quarterly | MD / Procurement | ID.AM-04, GV.SC-04 | Days 30–60 | Yes — Quarterly | Phase 2 | HIGH
RS-02 | Respond | Create client notification procedure defining who approves, who contacts the client, what information is shared, and maximum time to notify when client data is exposed | Operations Manager | RS.CO-02, RS.CO-03 | Days 45–90 | Yes — Annual review | Phase 2 | MEDIUM
GV-03 | Govern | Implement monthly cybersecurity risk dashboard reporting top risks, owners, actions taken, and overdue items to leadership | Risk Owner | GV.OV-01, GV.OV-03 | Days 30–60 | Yes — Monthly | Phase 2 | MEDIUM
ID-03 | Identify | Conduct formal cybersecurity risk assessment twice yearly using the existing risk register as the starting point. Review assets, threats, controls, ratings, and gaps | Risk Owner | ID.RA-04, ID.RA-05 | Days 90–180 | Yes — Twice yearly | Phase 3 | MEDIUM
PR-04 | Protect | Deliver cybersecurity awareness training for all staff covering phishing, password safety, device loss, data handling, and incident reporting. Repeat every six months with a one-page reference guide | Risk Owner | PR.AT-01, PR.AT-02 | Days 90–120 | Yes — Every 6 months | Phase 3 | MEDIUM
RC-02 | Recover | Create business continuity checklist identifying critical operations, recovery owners, backup contact methods, record locations, and maximum acceptable recovery time for each critical process | Operations Manager | RC.RP-01, RC.BC-01 | Days 90–180 | Yes — Annual review | Phase 3 | MEDIUM
Phase 1: 6 actions ¦ 0–30 days |  |  | Phase 2: 7 actions ¦ 30–90 days |  |  | Phase 3: 3 actions ¦ 90–180 days
Fensis Limited ¦ Cybersecurity Strategy and GRC Improvement Roadmap ¦ NIST CSF 2.0 ¦ Breck Agyekum — GRC Consultant

## Recurring Activities
RECURRING CYBERSECURITY ACTIVITIES — FENSIS LIMITED
These activities must be maintained continuously — cybersecurity is not a one-time project
ID | Function | Activity | Owner | Frequency | Next Review
GV-03 | Govern | Monthly cybersecurity risk dashboard — top risks, owners, actions, overdue items reported to leadership | Risk Owner | Monthly | Every month
DE-01 | Detect | Weekly security alert and login review across all business accounts | IT Manager / Risk Owner | Weekly | Every week
RC-01 | Recover | Weekly backup of critical records to cloud storage — verify new files are included | Risk Owner / IT | Weekly | Every week
PR-03 | Protect | Quarterly access review — confirm role-based access is correct. Remove access for departed or changed-role staff | Operations Manager | Quarterly | Every 3 months
ID-01 | Identify | Quarterly asset register review — update for new assets, vendors, systems, or role changes | Operations Manager | Quarterly | Every 3 months
ID-02 | Identify | Quarterly vendor dependency review — monitor Hikvision and Dahua geopolitical risk updates | MD / Procurement | Quarterly | Every 3 months
RC-01 | Recover | Quarterly restoration test — verify that backup files can actually be recovered | Risk Owner / IT | Quarterly | Every 3 months
ID-03 | Identify | Twice-yearly formal cybersecurity risk assessment using the risk register as the starting point | Risk Owner | Twice yearly | Every 6 months
PR-04 | Protect | Cybersecurity awareness training for all staff — phishing, password safety, device loss, data handling | Risk Owner | Every 6 months | Every 6 months
GV-02 | Govern | Annual review of Information Security and Data Handling Policy — update for business changes | Risk Owner | Annually | Every 12 months
RS-01 | Respond | Annual review and update of incident response plan — incorporate lessons from any incidents | Risk Owner | Annually | Every 12 months
RS-02 | Respond | Annual review of client notification procedure — update contacts and communication steps | Operations Manager | Annually | Every 12 months
RC-02 | Recover | Annual review of business continuity checklist — update critical operations, owners, and recovery times | Operations Manager | Annually | Every 12 months
Fensis Limited ¦ Cybersecurity Strategy and GRC Improvement Roadmap ¦ NIST CSF 2.0 ¦ Breck Agyekum — GRC Consultant